## Dropdown List (2) (hidden)
Drop Down Selection
High | Not started
Medium | In progress
Low | Complete

## Risk Register
Risk Register for EPCs |  | EPC-REG-RSK-001 | Rev 1
Risk Description | Impact Description | Probability of risk | Impact of risk | Mitigating actions | Mitigation owner | Due date | Status
e.g. Risk of equipment loss when doing inspections. | e.g. equipment is lost and inspection cannot be completed.This will result in re-work and purchase of replacement equipment creating additional cost for the company. | Medium | High | 1. Attach a lanyard to the laser meter 2. Develop a checklist to be completed after inspection to ensure equipment is kept safely after inspections 3. Develop an equipment log so that equipment is signed out and returned by personnel using equipment | John Doe | 2024-09-30 | Not started

## example (hidden)
| Project Name | [12 empty] | Project Identification Number (PIN) |  |  |  | Date:
| Project Manager | [15 empty] | Name of Risk Owner:
|  |  |  | QUALITATIVE ANALYSIS | [13 empty] | RISK RESPONSE | MONITOR and CONTROL
|  | RISK EVENT NAME: | unknown utilities | [10 empty] | 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | avoid
Status | Active Risk | RISK TRIGGER: | discovery | [10 empty] | 9 |  |  |  | avoid |  | Item of Interest | CTR | 20 | Right-of-way | change likelihood
|  | THREAT | [11 empty] | 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | change impact
RBS Category | UTL | Areas outside of R/W have not been investigated for conflicts. Additional work is required for sewer/storm, water, gas, power, communications. Triggers include: utilities found late in design or during construction. | [11 empty] | 7 |  |  |  | TO BE TAKEN | update at the next Quarterly Project Report (QPR) meeting | THREAT | ENV | 40 |  | share
[14 empty] | 6 | Medium |  |  | subsurface utility investigations immediately; assign team member to this full time. |  | OPPORTUNITY | MGT | 50 |  | accept
Risk Number | 20 | [12 empty] | 5 | [6 empty] | PSP | 60
[14 empty] | 4 | [6 empty] | ROW | 70
Project Phase | Design | [12 empty] | 3 | Low | [5 empty] | RR | 80
[11 empty] | X |  |  | 2 | [6 empty] | STG | 90
Date | May 32, 2929 | [12 empty] | 1 | Very Low | [5 empty] | UTL | 900
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 1
Risk Owner | M. Example |  |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  |  |  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
|  | RISK EVENT NAME: | noise wall | 1 RISK 1: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | avoid
Status | Active Risk | RISK TRIGGER: | analysis results | 1 RISK 1: 9 |  |  |  | avoid |  | Item of Interest | CTR | 20 | Right-of-way | change likelihood
|  | THREAT |  | 9: X; 1 RISK 1: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | change impact
RBS Category | ENV | possibility that a noise wall will have to be added to the project - pending results of the type 1 analysis; this is a high impact high probability threat |  | 1 RISK 1: 7 |  |  |  | TO BE TAKEN | analysis due August 39th. | THREAT | ENV | 40 |  | share
|  |  |  | 1 RISK 1: 6 | Medium |  |  | press for noise analysis ASAP |  | OPPORTUNITY | MGT | 50 |  | accept
Risk Number | 90 |  |  | 1 RISK 1: 5 | [6 empty] | PSP | 60
|  |  |  | 1 RISK 1: 4 | [6 empty] | ROW | 70
Project Phase | Design |  |  | 1 RISK 1: 3 | Low | [5 empty] | RR | 80
|  |  |  | 1 RISK 1: 2 | [6 empty] | STG | 90
Date | May 32, 2929 | [13 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 1
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 2
Risk Owner | Green Jeans |  |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  |  |  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
|  | RISK EVENT NAME: | cultural resources | 1 RISK 2: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | avoid
Status | Item of Interest | RISK TRIGGER: | discovery | 1 RISK 2: 9 |  |  |  | accept |  | Item of Interest | CTR | 20 | Right-of-way | change likelihood
|  | THREAT |  | 1 RISK 2: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | change impact
RBS Category | ENV | discovery of artifact; triggered during design if field investigation results in discovery; also trigger if discovered during construction ¦ deemed low probability - this area has been investigated previously and very little new ground is being disturbed. |  | 1 RISK 2: 7 |  |  |  | TO BE TAKEN | supplemental field investigation report due November 31. | THREAT | ENV | 40 |  | share
|  |  |  | 1 RISK 2: 6 | Medium |  |  | monitor |  | OPPORTUNITY | MGT | 50 |  | accept
Risk Number | 40 |  |  | 1 RISK 2: 5 | [6 empty] | PSP | 60
|  |  |  | 1 RISK 2: 4 | [6 empty] | ROW | 70
Project Phase | Design |  |  | 2: X; 1 RISK 2: 3 | Low | [5 empty] | RR | 80
|  |  |  | 1 RISK 2: 2 | [6 empty] | STG | 90
Date | May 33, 2929 | [13 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 3
Risk Owner | Green Jeans |  |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
X
X
X