## 2025 EEDSM Project Work Plan
ANNEXURE E
2027/28 Municipal EEDSM Activity Work Plan
Name of Municipality
Contact Person
Work Telephone / Mobile
Email Address:
EEDSM Measures
Overall Project Status (Tick one appropriate) | Started | Not Started
Project Implementation (Tick one appropriate) | Internal | Outsorced/External
|  |  |  | YEAR: 2026 | [23 empty] | YEAR: 2027
Municipal EEDSM Grant Project Activity Work Plan |  |  |  | Q1 | [11 empty] | Q2 | [11 empty] | Q3 | [11 empty] | Q4
|  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | De |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun
COMPONENT | OUTPUT | BUDGET (**) | ACTIVITIES | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4
1. EEDSM grant Projects Administration | 1.1. Signed EEDSM grant Memorandum of Agreement and EEDSM grant Workplan (Excel Spreadsheet) | R | 1.1.2. Obtain internal approval and signature from the Accounting Officer
| 1.2. Finalised appointment of a Project Manager for the coordination and reporting of the implementation of the EEDSM projects | R | 1.2.1. Include the scope of work of the EEDSM grant 2.0 Project in the job description
| 1.3. EEDSM grant Business Plan (Excel Spreadsheet) and Narrative Business Case for the allocated grant fund including the outer two (2) financial years | R | 1.3.1. Review the EEDSM Grant 2.0 Project Business Plan (Excel Spreadsheet) and Narrative Business Case Templates
| 1.4. Established and functional Municipality's EEDSM Project Steering Committee | R | 1.4.1. Develop Standardised Terms of Reference (ToRs) for the EEDSM Grant 2.0 Project Steering Committee
1.4.2. Coordinate and facilitate the EEDSM grant 2.0 Project Steering Committee.
| 1.5. Appoint one (1) graduate and/or technican per million rand allocated to support EEDSM grant Projects implementation. | R | 1.5.1. Recruitment and appointment of graduates/technicians to support the EEDSM grant 2.0 project's implementation.
| 1.6. Attend and present in the EEDSM grant Programme Steering Committee organised by the Department of Electricity and Energy. | R | 1.6.2. Prepare and present a presentation for the EEDSM grant 2.0 Programme Steering Committee
2. EEDSM grant Projects Planning | 2.1. Finalised procurement and appointment of a Technical Consultant (TC) to conduct energy audits, issue of Energy Performance Certificates, and create an inventory of Buildings and Infrastructure. | R | 2.1.1. Develop Terms of Reference/Bid Document for the TC to support in conducting energy audits and finalisation of the inventory of facilities.
2.1.2. Procure services of the Technical Consultant (TC) to conduct energy audits in Buildings and WWTWs
| 2.2. Consolidated Inventory of Buildings & Infrastructure | R | 2.2.1. Develop a template for the inventory of the municipality's facilities
2.2.2. Engage the unit responsible for the Municipality's Asset Register to determine the existence of an Asset Register
2.2.3. Conduct walk-through audits and facility visits to collect data required for the facilities’ building asset register
| 2.3. Completed Energy Audits of Buildings and Infrastructure. | R | 2.3.1. Update/develop the energy audit templates for Buildings & WWTWs (Report & Excel Spreadsheets) to be used by the TC
2.3.2. Conduct walk-through and detailed energy audits in targeted Buildings & WWTWs
| 2.4. Assessed Energy Performance of Buildings and Energy Performance Certificates Issued. | R | 2.4.1. Identify and register additional buildings that still require Energy Performance Certificates (EPCs) in the National Building Energy Performance Register (NBEPR)
2.4.2. Use the Energy Audits Reports of Buildings to issue Energy Performance Certificates (EPCs)
| 2.5. Developed Project Concept with Possible Energy Efficiency (EE) and Demand Side Management (DSM) measures for three (3) financial years. | R | 2.5.1. Review/develop a template for the EEDSM Project Concept
2.5.2. Use the energy audit reports (WWTWs) to develop the EEDSM Concepts with high-level financial requirements for 3 years.
| 2.6. Developed EEDSM financing strategy and instruments for the EEDSM measures and introduction of Energy Performance Contracting (EnPC) Model. | R | 2.6.1. Conduct a financial analysis to determine the funding and policy instruments required for the prepared EEDSM Project Concepts
2.6.2. Develop a financial strategy for the introduction of the EnPC Model for targeted Buildings & WWTWs
3. EEDSM grant Projects Implementation | 3.1. Finalised procurement and appointment of Transactional Advisor (TA) to support the development of the Business Case for the Energy Performance Contracting (EnPC) Project | R | 3.1.1. Develop Terms of Reference/Bid Document for the appointment of the TA to support the Municipality in preparing the Business Case of the EnPC Projects
|  | R | 3.1.2. Procure service for Transaction Advisor (TA) to support the development of EnPC Project for buildings and infrastructure
| 3.2. Developed EnPC Project with detail financial analysis with the support of the appointed Transactional Advisor (TA). | R | 3.2.1. Review the Energy Audits and EEDSM measures prepared by the TC to prepare the concepts for the EnPC Projects (1-2) with the support of the TA
|  | R | 3.2.2. Develop a proposed EnPC for the Buildings and infrastructure with the support of the TA and TC.
|  | R | 3.2.3. Develop a bespoke/customised contract for the EnPC Projects, including functional, empowerment, and financial evaluation criteria
|  | R | 3.2.4. Request approval of the EnPC Projects with the proposed contract model and evaluation criteria for procurement.
|  | R | 3.2.5. Prepare and issue the Tender Documents for the EnPC Projects with the support of the TA
|  | R | 3.2.6. Engage National Treasury and conduct Stakeholder Consultation in line with Section 33 of MFMA for EnPC Projects that have more 3 years payback period
| 3.3. Finalised procurement appointment of an Energy Service Company (ESCO) Contractor for the implementation of the EEDSM grant project activities. | R | 3.3.1. Prepare bid documents to appoint the ESCo Contractor/Supplier for the energy efficient technologies
3.3.2. Evaluate the Bids for the appointment of the ESCO Contractor/Supplier and finalise the Service Level Agreement (SLA)
| 3.4. Completed retrofits for the municipality's buildings and infrastructure with energy-efficient and alternative clean energy technologies using the allocated EEDSM grant. | R | 3.4.1. Issue an order/purchase number for the ESCO Contractor/Supply to supply and deliver the energy efficient technologies
|  | R | 3.4.2. Installation of the energy efficient technologies within the targeted facilities/infrastructure
3.4.3. Measurement & Verification (M&V) of installed energy efficient technologies and achieved energy savings by DEE
| 3.5. Developed and implemented Capacity Building and Training Plan. | R | 3.5.1. Review and update the Institutional Assessment Tool for application within the municipality
|  | R | 3.5.2. Conduct an institutional assessment to determine the capacity needs and gaps to develop and monitor the implementation of the EEDSM grant 2.0 Programme.
|  | R | 3.5.3. Update the Capacity Building and Training Framework and Plan
|  | R | 3.5.4. Implement the Capacity Building and Training Plan.
| 3.6. Created and maintained database of trained graduates/technicians | R | 3.6.1. Capture information of the Trainees and track training delivered and achievements
| 3.7. Developed and implemented EEDSM awareness plan with a focus on schools, community and within the municipality. | R | 3.7.1. Updated/developed Awareness Raising Framework
|  | R | 3.7.2. Develop an Awareness Raising Plan and Schedule covering targeted schools, community, SMMEs and Officials
|  | R | 3.7.3. Implement the Awareness Raising Plan and Schedule covering targeted schools, community, SMMEs and Officials
4. EEDSM grant Projects Monitoring, Verification and Reporting (MRV) process | 4.1. Installed smart metering technologies and energy management system to support the tracking of energy consumption and savings. | R | 4.1.1. Development of technical specifications for the supply, installation and smart meters with a communication backend
|  | R | 4.1.2. Procurement of services for the supply and installation of smart meters
|  | R | 4.1.3. Installation of smart meters
| 4.2. Established Monitoring, Reporting & Verification (MRV) process and dashboard for tracking of performance of installed technologies, energy consumption baselines and energy savings. | R | 4.2.1. Develop an MRV framework outlining gaps, key performance indicators, and solutions for tracking performance on key metrics in excel format
|  | R | 4.2.2. Development of a dashboard for monitoring the performance of the installed technologies in line with key performance indicators.
|  | R | 4.2.3. Monthly and quarterly reporting
|  | R | 4.2.4. Independent Measurement and Verification of achieved KPIs
| 4.3. Report on the utilisation of the MEMS tool | R | 4.3.1. Alignment of the MEMS tool with MRV dashboard
|  | R | 4.3.2. Collation and capturing of billing data of the facilities in a format compatible to the MEMS Tool
TOTAL |  | 0
(*) Project activities are indicative, and are to be adopted to specific activities
(**) Budget to reflected should be indicative subject to approval of the EEDSM Project Business Plan